## Sheet1
|  |  | Total Hours |  |  | Total Cost |  |  | Project Manager | [5 empty] | Frontend Developer | [5 empty] | Backend Developer | [5 empty] | Data Scientist | [5 empty] | Data Engineer
Task Id | Task | Predecessor Task ID | Best Case | Expected | Worst Case | Best Case | Expected | Worst Case | Best | Expected | Worst | $ Best | $ Expected | $ Worst | Best | Expected | Worst | $ Best | $ Expected | $ Worst | Best | Expected | Worst | $ Best | $ Expected | $ Worst | Best | Expected | Worst | $ Best | $ Expected | $ Worst | Best | Expected | Worst | $ Best | $ Expected | $ Worst
A | Describe product |  | 10 | 15 | 20 | 1100 | 1650 | 2200 | 10 | 15 | 20 | 1100 | 1650 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | Develop marketing strategy |  | 12 | 18 | 24 | 1320 | 1980 | 2640 | 12 | 18 | 24 | 1320 | 1980 | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Design brochure | A | 8 | 12 | 16 | 880 | 1320 | 1760 | 8 | 12 | 16 | 880 | 1320 | 1760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | Develop product prototype |  | 195 | 245 | 335 | 18955 | 24080 | 32280 | 28 | 36 | 49 | 3080 | 3960 | 5390 | 47 | 59 | 78 | 4465 | 5605 | 7410 | 48 | 59 | 80 | 5040 | 6195 | 8400 | 17 | 22 | 28 | 1870 | 2420 | 3080 | 45 | 59 | 80 | 4500 | 5900 | 8000
D1 | Requirements analysis | A | 20 | 25 | 35 | 2140 | 2660 | 3730 | 12 | 14 | 21 | 1320 | 1540 | 2310 | 2 | 3 | 4 | 190 | 285 | 380 | 2 | 3 | 4 | 210 | 315 | 420 | 2 | 2 | 2 | 220 | 220 | 220 | 2 | 3 | 4 | 200 | 300 | 400
D2 | Software design | D1 | 30 | 40 | 50 | 3060 | 4070 | 5080 | 5 | 6 | 7 | 550 | 660 | 770 | 8 | 11 | 14 | 760 | 1045 | 1330 | 8 | 11 | 14 | 840 | 1155 | 1470 | 1 | 1 | 1 | 110 | 110 | 110 | 8 | 11 | 14 | 800 | 1100 | 1400
D3 | System design | D1 | 40 | 50 | 70 | 3060 | 4070 | 5080 | 5 | 6 | 7 | 550 | 660 | 770 | 8 | 11 | 14 | 760 | 1045 | 1330 | 8 | 11 | 14 | 840 | 1155 | 1470 | 1 | 1 | 1 | 110 | 110 | 110 | 8 | 11 | 14 | 800 | 1100 | 1400
D4 | Coding | D2, D3 | 45 | 55 | 75 | 4550 | 5570 | 7590 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 16 | 22 | 1330 | 1520 | 2090 | 14 | 16 | 22 | 1470 | 1680 | 2310 | 5 | 7 | 9 | 550 | 770 | 990 | 12 | 16 | 22 | 1200 | 1600 | 2200
D5 | Write documentation | D4 | 20 | 25 | 35 | 2050 | 2570 | 3610 | 3 | 4 | 6 | 330 | 440 | 660 | 5 | 6 | 8 | 475 | 570 | 760 | 5 | 6 | 8 | 525 | 630 | 840 | 2 | 3 | 5 | 220 | 330 | 550 | 5 | 6 | 8 | 500 | 600 | 800
D6 | Unit testing | D4 | 15 | 20 | 30 | 1530 | 2035 | 3045 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 9 | 380 | 570 | 855 | 4 | 5 | 8 | 420 | 525 | 840 | 3 | 4 | 5 | 330 | 440 | 550 | 4 | 5 | 8 | 400 | 500 | 800
D7 | System testing | D6 | 15 | 18 | 25 | 1525 | 1845 | 2570 | 1 | 2 | 3 | 110 | 220 | 330 | 4 | 4 | 5 | 380 | 380 | 475 | 5 | 5 | 7 | 525 | 525 | 735 | 1 | 2 | 3 | 110 | 220 | 330 | 4 | 5 | 7 | 400 | 500 | 700
D8 | Package deliverables | D5, D7 | 10 | 12 | 15 | 1040 | 1260 | 1575 | 2 | 4 | 5 | 220 | 440 | 550 | 2 | 2 | 2 | 190 | 190 | 190 | 2 | 2 | 3 | 210 | 210 | 315 | 2 | 2 | 2 | 220 | 220 | 220 | 2 | 2 | 3 | 200 | 200 | 300
E | Survey potential market | B, C | 10 | 16 | 20 | 1100 | 1760 | 2200 | 5 | 8 | 10 | 550 | 880 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 10 | 550 | 880 | 1100 | 0 | 0 | 0 | 0 | 0 | 0
F | Develop pricing plan | D8, E | 8 | 10 | 16 | 880 | 1100 | 1760 | 4 | 5 | 8 | 440 | 550 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 8 | 440 | 550 | 880 | 0 | 0 | 0 | 0 | 0 | 0
G | Develop implementation plan | A, D8 | 5 | 7 | 10 | 535 | 755 | 1070 | 3 | 5 | 6 | 330 | 550 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 105 | 105 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 100 | 100 | 200
H | Write client proposal | F, G | 3 | 5 | 7 | 330 | 550 | 770 | 3 | 5 | 7 | 330 | 550 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 251 | 328 | 448 | 25100 | 33195 | 44680 | 73 | 104 | 140 | 8030 | 11440 | 15400 | 47 | 59 | 78 | 4465 | 5605 | 7410 | 49 | 60 | 82 | 5145 | 6300 | 8610 | 26 | 35 | 46 | 2860 | 3850 | 5060 | 46 | 60 | 82 | 4600 | 6000 | 8200
Assumptions
All contractors will be working remotely and would use their own hardware (laptops, monitors ..)
All contractors have at least 10 years of experience
Best Case = all stories/features are completed with no major issues or blocks.
Expected Case = all storied/features are completed with some issues and blocks which are resolved in time.
Worst Case = storied/features experience major challenges and delays (internal or external).
The tasks breakdown above allocates total hours required for each task (best, expected, worst) and then provides individual roles contribution towards that total.
Hourly rates are presented below for each role:
| Role | Hourly Rate
| Project Manager | 110
| Frontend Developer | 95
| Backend Developer | 105
| Data Engineer | 100
| Data Scientist | 110